## Agile Resource Plan
AGILE RESOURCE PLANNING TEMPLATE
RESOURCE | NAME | STATUS | START DATE | END DATE | DURATION in days | COMMENTS
Project Manager | Steve C. | Complete | 2022-01-16 | 2022-01-21 | 5
Designer | Claudia K. | Complete | 2022-01-18 | 2022-01-21 | 3
Quality Assurance | Paul B. | In Progress | 2022-01-22 | 2022-01-23 | 1
Business Analyst | Kevin D. | On Hold | 2022-01-22 | 2022-01-23 | 1
Marketing Manager | Kelly K. | Not Started | 2022-01-22 | 2022-01-28 | 6
Software Developer | Ryan H. | Not Started | 2022-01-27 | 2022-01-29 | 2
Tester | Maura T. | Not Started | 2022-01-28 | 2022-02-04 | 7
Database Administrator | Chantelle C. | Not Started | 2022-02-05 | 2022-02-09 | 4
Resource 7 | Staff 7 | Not Started | 2022-01-28 | 2022-02-05 | 8
Resource 8 | Staff 8 | Not Started | 2022-02-04 | 2022-02-06 | 2
Resource 9 | Staff 9 | Not Started | 2022-02-07 | 2022-02-10 | 3
Resource 10 | Staff 10 | Not Started | 2022-02-09 | 2022-02-12 | 3
Resource 11 | Staff 11 | Not Started | 2022-02-11 | 2022-02-14 | 3
Resource 12 | Staff 12 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 13 | Staff 13 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 14 | Staff 14 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 15 | Staff 15 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 16 | Staff 16 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 17 | Staff 17 | Not Started | 2022-02-15 | 2022-02-17 | 2

## Agile Resource Plan- BLANK
AGILE RESOURCE PLANNING TEMPLATE
RESOURCE | NAME | STATUS | START DATE | END DATE | DURATION in days | COMMENTS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options. * Delete any unpopulated rows in your table. *